## Managament Summary
| Total |  |  | Coding |  |  | Meetings
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Amanda | 6700 | 6650 | 50 | 5700 | 3600 | 2100 | 1000 | 3050 | -2050
Tyrel | 4400 | 8050 | -3650 | 3400 | 5400 | -2000 | 1000 | 2650 | -1650
Austin | 2300 | 8250 | -5950 | 1300 | 5600 | -4300 | 1000 | 2650 | -1650
Tristan | 5200 | 6350 | -1150 | 4200 | 3700 | 500 | 1000 | 2650 | -1650
Total | 18600 | 29300 | -10700 | 14600 | 18300 | -3700 | 4000 | 11000 | -7000

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned
Amanda |  |  | hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
generate camera | 3 | 2 | bar: 3
create terrain | 6 | 4 | bar: completed 6
create skybox | 3 | 1 | bar: completed 9
track score and lives | 6 | 7 | bar: completed 12 to this week 18
create scenery for levels | 24 | 12 | bar: this week 21 to planned 42
exceptions for BC mode | 9 | bar: planned 45 to planned 51
testing | 6 | 10 | bar: planned 54 to planned 60
totals | 57 | 36 | bar: planned 63 to planned 69
Tyrel
Software Analysis Presentation | 5 | 7 | bar: 3 to completed 9
local source implementation | 2 | 3 | bar: completed 12
Internet source implementation | 3 | bar: this week 15
implement text to speech | 5 | bar: this week 18 to this week 21
user documentation | 5 | 6 | bar: planned 24 to planned 27
programming | 10 | 24 | bar: planned 30 to planned 51
testing | 3 | 14 | bar: planned 54 to planned 66
installation | 1 | bar: planned 69
totals | 34 | 54
Austin
determine required menus | 1 | 4 | bar: 3
design menus | 2 | 7 | bar: completed 6 to completed 12
program menus | 5 | 18 | bar: this week 15 to planned 30
program saving score | 2 | 4 | bar: planned 33 to planned 36
integrate | 2 | 11 | bar: planned 39 to planned 48
testing | 1 | 12 | bar: planned 51 to planned 66
totals | 13 | 56
Tristan
outline of game | 9 | 12 | bar: 3 to completed 12
ball generation | 9 | 7.5 | bar: this week 15 to this week 18
ball features | 9 | 8.5 | bar: this week 21 to planned 30
testing | 3 | 5 | bar: planned 33 to planned 36
power up targets | 6 | bar: planned 39 to planned 42
balancing | 6 | 4 | bar: planned 45 to planned 48
totals | 42 | 37
group totals (hrs) | 146 | 183
group totals ($) | 14600 | 18300

## Meetings
| Date | Aug. 30 | Sept. 1 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1.5 | 4 | 2 | 2 | 2 | 2 | 2 | 6 | 1 | 8
Amanda | 30.5 | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Tyrel | 26.5 | ü | ü | ü | ü | ü |  |  | ü | ü | ü
Austin | 26.5 | ü | ü | ü | ü |  | ü |  | ü | ü | ü
Tristan | 26.5 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Total | 110 | 6 | 16 | 8 | 8 | 4 | 4 | 4 | 24 | 4 | 32
ü

## RFP
| Task | scheduled(hrs) | spent(hrs)
Amanda | Individual schedule | 2 | 2
| Chapter 1 and 2, glossary Terms | 4 | 5
| Subtotal | 6 | 7
Tyrel | Individual schedule | 2 | 3
| Chapter 3 and 4, glossary Terms | 4 | 5
| Subtotal | 6 | 8
Austin | Individual schedule | 1 | 1
| Merge schedules on google docs | 2 | 2
| Standardize formating | 1 | 1
| Assemble SA Powerpoint | 2 | 3
| Subtotal | 6 | 7
Tristan | Individual schedule | 2 | 2
| Chapter 5 and 6, glossary Terms | 4 | 5
| Subtotal | 6 | 7
| Total | 24 | 29
red is dependent on others