## Sheet1
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned
Amanda |  |  | hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
generate camera | 3 | 2 | bar: 3
create terrain | 6 | 4 | bar: completed 6
create skybox | 3 | 1 | bar: completed 9
track score and lives | 6 | 7 | bar: completed 12 to this week 18
create scenery for levels | 24 | 12 | bar: this week 21 to planned 42
exceptions for BC mode | 9 | bar: planned 45 to planned 51
testing | 6 | 10 | bar: planned 54 to planned 60
totals | 57 | 36 | bar: planned 63 to planned 69
Tyrel
Software Analysis Presentation | 5 | 7 | bar: 3 to completed 9
local source implementation | 2 | 3 | bar: completed 12
Internet source implementation | 3 | bar: this week 15
implement text to speech | 5 | bar: this week 18 to this week 21
user documentation | 5 | 6 | bar: planned 24 to planned 27
programming | 10 | 24 | bar: planned 30 to planned 51
testing | 3 | 14 | bar: planned 54 to planned 66
installation | 1 | bar: planned 69
totals | 34 | 54
Austin
determine required menus | 1 | 4 | bar: 3
design menus | 2 | 7 | bar: completed 6 to completed 12
program menus | 5 | 12 | bar: this week 15 to planned 30
program saving score | 2 | bar: planned 33 to planned 36
integrate | 2 | 11 | bar: planned 39 to planned 48
testing | 1 | 10 | bar: planned 51 to planned 63
totals | 13 | 44
Tristan
outline of game | 9 | 12 | bar: 3 to completed 12
ball generation | 9 | 7.5 | bar: this week 15 to this week 18
ball features | 9 | 8.5 | bar: this week 21 to planned 30
testing | 3 | 5 | bar: planned 33 to planned 36
power up targets | 6 | bar: planned 39 to planned 42
balancing | 6 | 4 | bar: planned 45 to planned 48
totals | 42 | 37
group totals (hrs) | 146 | 171
group totals ($) | 14600 | 17100